## Slide 1: ANGELS ONLINE EVENTS GUIDELINE
Many Learnings of On-the-line Events to Make Benefit Glorious Initiative of Angels
28.5.2020 (v1.0)

## Slide 2: Classification of Angels Online Events
WEBINAR
WORKSHOP
CONSULTANCY

## Slide 3: Classification of Angels Online Events
WEBINAR
ONE-WAY COMMUNICATION
EQUIVALENT TO SEMINARS OR SYMPOSIUMS
TOPICAL THEME OR SUBJECT
(E.G. COVID-19, GUIDELINES, COUNTRY REPORT)
CONSULTANCY
PERSONAL COMMUNICATION
VARIOUS TOPICS
EQUIVALENT TO HOSPITAL, COORDINATION OR COMMITTEE MEETINGS
SMALL AUDIENCE (1 – 15 pax)
WORKSHOP
INTERACTIVE COMMUNICATION
SMALL TO MEDIUM AUDIENCE (3 – 100 pax.)
EQUIVALENT TO ANGELS DAY, TTT, EMS
OR NURSE WORKSHOPS
FRAMED WITHIN THE ANGELS 4 PRIORITY ACTIONS
GOAL: DISSEMINATE INFORMATION
MEDIUM TO LARGE AUDIENCE (50 – 1,000 pax)
GOAL: CHANGE IN BEHAVIOR & PRACTICE
GOAL: COORDINATE & MONITOR IMPLEMENTATIONS

## Slide 4: Connection Methods
ONLINE MEETING
PARTICIPANTS
DIRECT WEBINAR
PARTICIPANTS
SPEAKERS
BROADCAST WEBINAR
SPEAKERS
PARTICIPANTS
TECHNICIANS

## Slide 5: Planning an Angels Webinar & Workshop
SPEAKER MANAGEMENT
CONTRACTS & VIDEO CONSENT
CONTENT BRIEFING SESSION
SLIDES REVIEW & SUBMISSION
REMOTE PRESENTER BRIEFING GUIDE
LOGISTICS MANAGEMENT
AGENCY BRIEFING SESSION
INVITATION DESIGN & REVIEW
PLATFORM DESIGN & REVIEW
PLATFORM TESTING
TECHNICAL MEETING
PLATFORM WALKTHROUGH
CONNECTION, AUDIO & VIDEO CHECK
MITIGATION PLANS
TECHNICAL REHEARSAL
LIVE EVENT
FINAL TECHNICAL CHECK (H-1)
HOUSEKEEPING NOTES
EVENT MANAGEMENT
TECHNICAL TROUBLESHOOTING
CONTENT COORDINATION
(Define your agenda incl. dates, programmes, speakers & moderators)
FOLLOW-UP
THANK YOU EMAIL
DEBRIEFING SESSION
PARTICIPANT ENGAGEMENT
D-2
D-0
D+1 to D+7
D-21 to D-2
D-∞
INVITATION & REGISTRATION
OPEN VS CLOSED ATTENDANCE
SENDGRID VS PERSONAL INVITE
OTHER DISSEMINATION CHANNELS
INTERACTIVITY
LIVE POLLING
VIRTUAL TRAINING TOOLS
Q&A / PANEL DISCUSSION
REGISTRATION
OPEN ATTENDANCE
Agencies must create any kind of form for viewers to indicate speciality
REGISTRATION
CLOSED ATTENDANCE
Keep invitation list and categorize the participant by speciality

## Slide 6: Helsinki Ingelheim Measures 12 measures to optimize online event pathways
LESS IS MORE
THE MORE SPEAKERS, THE MORE TECHNICAL COMPLICATIONS. FOUR SPEAKERS IS A GOOD NUMBER FOR A 2-3 HOURS SESSION.
1
SPEAKER COORDINATION
ORGANIZE A MEETING WITH ALL SPEAKERS TO INTRODUCE EACH OTHER, DISCUSS CONTENT, EXPECTATIONS AND NEXT STEPS.
2
QUESTION SEEDING
WHEN PLANNING A Q&A OR PANEL DISCUSSION SESSION, PREPARE UP TO 5 MOST LIKELY ASKED QUESTIONS IN ADVANCE.
3
MITIGATION PLANNING
ESTABLISH AND TEST BACKUP SOLUTIONS, E.G. ALTERNATE CONNECTION FOR SPEAKERS, BACKUP STREAMING CHANNEL.
4
FILLER CONTENT
PREPARE CONTENT FOR USE IN CASE OF TECHNICAL PROBLEM, E.G. ANGELS VIDEOS, „BE RIGHT BACK“ GRAPHICS, PHOTO OF SPEAKER.
5
INVITATION
SENDGRID IS GREAT FOR MASS EMAILING BUT PERSONAL APPROACH IS MORE EFFECTIVE. TAKE ADVANTAGE OF OUR NETWORK/PARTNERS.
6
REGISTRATION & ATTENDANCE
THROUGH THE (PRE)REGISTRATION, ASK PARTICIPANT FOR AT LEAST THEIR NAME, EMAIL AND SPECIALITY AS AN ACCESS MECHANISM.
7
TECHNICAL MEETING
CONDUCT A THOROUGH TECHNICAL CHECK WITH ALL SPEAKERS FOLLOWED BY A SHORT REHEARSAL AT LEAST ONE DAY BEFORE.
8
BACKSTAGE COMMUNICATION
ENSURE THERE’S A SEPARATE COMMUNICATION CHANNEL BETWEEN MODERATOR, SPEAKERS, COORDINATOR AND TECHNICAL TEAM.
9
EVENT COORDINATOR
ASSIGN A FINAL DECISION MAKER FOR IF / WHEN A SITUATION CALLS FOR IT, E.G. SWAPPING AGENDA, PLAYING FILLER VIDEO, ETC.
10
SATISFACTION SURVEY
DON’T MISS THE OPPORTUNITY OF GETTING VALUABLE PARTICIPANT FEEDBACK TO IMPROVE YOUR NEXT EVENT.
11
FOLLOW UP
GREAT SUCCESS.
12