## Slide 1
30 – 60 – 90 days Review

## Slide 2: 30-60-90 Day Review
STRUCTURED FOLLOW-UP FOR SUSTAINED IMPACT
A structured follow-up framework aligned with Lean principles of Kaizen (continuous improvement).
Consultants revisit the hospital at:
Initial progress check and early adjustments
Each visit includes an after action review (AAR) to reflect on progress, challenges, and next steps.
Enables data-driven decision-making, accountability, and team empowerment.
Mid-point review to reinforce or recalibrate actions
Sustainability check and transition to autonomy
DAY 30
DAY 60
DAY 90

## Slide 3: After Action Review (AAR)
WHAT ARE WE GOING TO DO ABOUT IT?
WHY DID IT HAPPEN?
WHAT ACTUALLY HAPPENED?
WHAT DID THE TEAM SET OUT TO DO?
AAR is a structured method for team reflection, widely used in lean and high-performance environments
4 KEY QUESTIONS

## Slide 4: Question 1. What Did the Team Set Out to Do?
TASK | OWNER | DATE TO BEGIN | DUE DATE
EMS and hospital meeting | Dr Brown | 09 August 2025 | 10 September 2025
Implement EMS checklists | Dr James | 09 August 2025 | 11 September 2025
Identify direct ED/Stroke Unit numbers (bypass general reception) | Nurse Anna | 09 August 2025 | 12 September 2025
Create a stroke whatsapp group | Dr Bingley | 09 August 2025 | 13 September 2025

## Slide 5: Question 2. What Actually Happened?
DID WE ACHIEVE THE PROJECT OBJECTIVES?
STRENGHTS
What went right?
What was found to be particularly useful?
Did the teams come up with any new innovations?
What about the final product – is it great?
Were any new skills learned?
WEAKNESSES
What problems were encountered?
What were the effects of key problem areas (e.g. on budget, schedule, etc.)
Did we identify these problems as risks?
What could we have done differently?
Is there anything in the final work-product that could have been improved?

## Slide 6: Question 2. What Actually Happened?
TASK | OWNER | DATE TO BEGIN | DUE DATE | STATUS
EMS and hospital meeting | Dr Brown | 09 August 2025 | 10 September 2025 | Complete
Implement EMS checklists | Dr James | 09 August 2025 | 11 September 2025 | In Progress
Identify direct ED/Stroke Unit numbers (bypass general reception) | Nurse Anna | 09 August 2025 | 12 September 2025 | On Hold
Create a stroke whatsapp group | Dr Bingley | 09 August 2025 | 13 September 2025 | Delayed

## Slide 7: Question 3. Why Did it Happen?
Notes: Untitled Slide Then the third question: Why did it happen? For this, we want to use Root Cause Analysis, also known as RCA. It's a method of problem solving used for identifying the Root Cause of faults or problems. It is going to trace a problem into its origins, or "underlying causes", to entirely prevent problem recurrence. Here, you may like to differentiate "causal factors" and "Root causes". Causal factors affect an event's outcome but may not be a root cause, so it may not prevent problem recurrence with certainty if you only remove such causal factors. Like a doctor diagnosing a disease, "fever" is sometimes only the symptom of the real disease, because many diseases may show fever, from a common cold to several serious diseases. The doctor always takes actions to look for the real causes of the disease other than only treat the symptom of fever.

## Slide 8: Question 4. What are we Going to do About it?
Creative brainstorming
WHAT - IDEA
HOW - ACTION
WHO - OWNER
WHEN - DEADLINE
ACTION PLAN
Transform ideas into recommendations to improve future performance (avoid previous faults & leverage strengths)
Identify timing and owners for each action to be implemented

## Slide 9: Question 4. What are we Going to do About it?
WHAT - IDEA
HOW - ACTION
WHO - OWNER
WHEN - DEADLINE
ACTION PLAN